Project Documentation Research Lab Donnstags-Nachrichten

Market Integration Zurich–Basel, 1740 to 1842 · organised along the planning framework

Gregor Lushaj · Version 1.0.4 · As of 29 October 2026

| Project | Research Lab “Donnstags-Nachrichten (Zurich, 1730 to 1842)”, Individual Learning Unit, 6 ECTS |
| --- | --- |
| Research question | Was there market integration between the grain markets of Zurich and Basel around 1740, and how did it develop until 1842? |
| Supervision | Prof. Ulrich Woitek, Jakob Metzler |
| Student | Gregor Lushaj, student ID 23-915-812 |
| Duration and submission | 1 August 2026 to 31 January 2027; submission planned for Friday, 29 January 2027 |
| Credit transfer | Master, elective area OEC; condition: additional price data (Zurich series in the format of the price database) |
| Authoritative basis | Meeting of 7.10.2026 · Confirmation by email of 12.10.2026 · Planning framework of 14.10.2026 · Decisions of 15.10. and 26.10.2026 (section 9.1) |
| Working environment | Python with uv in PyCharm; Quarto CLI for writing only (check reports, essay, codebook); code in the private GitHub repository; management via GitHub Projects |
| Next gate | M2 on Sunday, 1 November 2026: Does the Zurich series hold up around 1740? |

About this document: It replaces the “Dokumentation Donnerstag-Nachrichten” (as of 15 October 2026) as the running project documentation; the earlier version is kept as an archive. It is structured along the planning framework of 14 October 2026: chapters 2 to 6 follow the PPDAC phases, within them chapters 4 and 5 follow the steps of the R4DS cycle with PDCA validation, chapter 6 the TIER structure and the Template README, chapter 7 project management and chapter 8 Gibbs’ Reflective Cycle. Chapter 10 breaks everything down into a checklist up to submission.

The rationale for the choice of models is given in the planning framework and is not repeated here. Only what is needed for planning, implementation and evidence has been carried over from the earlier documentation; the September concept is summarised in section 2.2 as the first PPDAC iteration.

Contents

1. Approach and Structure	4

1.1 The Framework at a Glance	4

1.2 Rules for Maintaining the Documentation	4

1.3 PPDAC as the Project’s Phase Model	4

2. Problem	5

2.1 Research Question	5

2.2 First Iteration: From Concept to Reorientation	5

2.3 Scope	6

2.4 Agreed Basis and Open Points	6

3. Plan	6

3.1 Data Basis	6

3.2 Measurement Concept	7

3.3 Pre-specified Variants	8

3.4 Lean Data Management Plan	8

3.5 Risks	9

4. Data: Pipeline and Validation	9

4.1 Overview of Steps	10

4.2 Import: Issue Register	10

4.3 Tidy I: Rubric Mapping	10

4.4 Tidy II: Price Parser	11

4.5 Check: Validation	11

4.6 Transform: Weekly Series	11

4.7 PDCA Micro-cycle for Extraction	12

5. Analysis: Estimation and Presentation	12

5.1 Model: RLS Estimation	12

5.2 Visualize: Figures and Tables	13

5.3 Freezing the Results	13

6. Conclusion: Submission and Replication Package	13

6.1 Parts of the Submission	13

6.2 Essay: Outline along PPDAC	14

6.3 Folder Structure after TIER, Implemented with Quarto and uv	14

6.4 README after the Template README	15

6.5 Checking the Package	16

7. Project Management	16

7.1 Work Packages and Milestones	16

7.2 Gates: Check Questions and Decisions	17

7.3 Gantt Overview	18

7.4 Kanban Board in GitHub Projects	18

7.5 Weekly Rhythm	18

8. Reflection after Gibbs	19

8.1 Procedure	19

8.2 Entry M1: Reorientation (7 to 12 October 2026)	19

8.3 Entries M2 to M5 and Conclusion	20

9. Decision Log and Open Questions	21

9.1 Decision Log	21

9.2 Open Questions for the Supervisors	22

10. Checklist from Project Start to Submission	24

10.1 Legend	24

10.2 Overview of Work Packages	24

10.3 Coverage of the Assessment	25

10.4 Ongoing Tasks	25

10.5 WP0 Group Phase (7 July to 18 August 2026)	26

10.6 WP1 Concept and Reorientation (19 August to 15 October 2026)	27

10.7 WP2 Data Basis and Prototype (14 October to 1 November 2026)	27

10.8 WP3 Price Parser and Validation (2 to 29 November 2026)	30

10.9 WP4 Estimation (30 November 2026 to 3 January 2027)	32

10.10 WP5 Essay and Replication Package (4 to 29 January 2027)	34

Appendix A: Mapping to IPERKA	37

Appendix B: Confirmed Email of 12 October 2026	37

Appendix C: Change History	38

Appendix D: Research Data Use Agreement	38

Sources	38

# 1. Approach and Structure

## 1.1 The Framework at a Glance

Five elements structure the project. Each has a fixed place in this documentation and produces a specific artefact in the project. The rationale for the choice is given in the planning framework of 14 October 2026.

| Level | Model | Place in this documentation | Artefact in the project |
| --- | --- | --- | --- |
| Research logic | PPDAC (Wild and Pfannkuch 1999) | Chapters 2 to 6 | Project plan, essay outline |
| Data process | R4DS cycle with PDCA micro-cycle | Chapters 4 and 5 | Python pipeline, check reports, validation log |
| Reproducibility | TIER Protocol 4.0, Template README, lean DMP | Sections 3.4 and 6.3 to 6.5 | Replication package, README.md |
| Project management | Work packages, milestones, Gantt, Kanban | Chapters 7 and 10 | GitHub Projects, checklist |
| Reflection | Gibbs’ Reflective Cycle (Gibbs 1988) | Chapter 8 | Reflection entries, final part |

## 1.2 Rules for Maintaining the Documentation

- Authoritative: This document records direction, plan, decisions and status. The technical details of each pipeline step are in the check reports under reports/ and in docs/ in the repository. Chapters 4 to 6 define what must be there and refer to it.

- Plan and actual: Chapters 4 to 6 describe the planned state. Each step table has a “Status” row, filled in on completion with date, result and a reference to the check report.

- Decisions: Every deviation from the plan and every piece of feedback from the supervisors goes into the decision log with date and rationale (section 9.1). Only then is the plan adjusted.

- IDs: Tasks carry the number of the work package and a running number, e.g. 2.10. The same ID appears on the card in GitHub Projects and in the commit message.

- Rhythm: Weekly review on Sunday (section 7.5), Gibbs entry after every milestone (chapter 8), new version with an entry in the change history (Appendix C) at every milestone.

- Data: Neither this document nor cards, issues or commits contain extracts of the provided data (sections 2 and 3 of the agreement). References are made by issue ID and date.

## 1.3 PPDAC as the Project’s Phase Model

Chapters 2 to 6 follow the five phases. The table shows where the project stands and is updated at every milestone.

| Phase | Content in the project | Chapter | Period | Status |
| --- | --- | --- | --- | --- |
| Problem | Research question, scope, agreed basis | 2 | July to 12.10.2026 | completed (M1) |
| Plan | Data basis, measurement concept, variants, data management, risks | 3 | until 22.10.2026 | fixed, reviewed at every gate |
| Data | Import, Tidy, Validation, Transform | 4 | 14.10. to 29.11.2026 (WP2, WP3) | current |
| Analysis | Model, Visualize, sensitivity, benchmark episodes | 5 | 30.11. to 23.12.2026 (WP4) | open |
| Conclusion | Essay, replication package, Zurich series, data documentation | 6 | 4.1. to 29.1.2027 (WP5) | open |

Returns to earlier phases are planned for. If the Data phase reveals a gap in the plan, the plan is changed through the decision log, not silently bypassed. The first return was the reorientation in October (section 2.2).

# 2. Problem

## 2.1 Research Question

Was there market integration between the grain markets of Zurich and Basel around 1740, and how did it develop until 1842?

Integration is measured by the correlation of weekly price changes in both cities. It is estimated by recursive least squares (RLS) as a time series of correlation coefficients. A correlation that rises over time indicates increasingly connected markets. The Zurich series comes from the official price quotations of the Donnstags-Nachrichten; the Basel series is available from the Avis project. The base price is Kernen (spelt). Further goods are added once their data quality in both cities supports a comparison.

## 2.2 First Iteration: From Concept to Reorientation

The concept of 18 September 2026 proposed a business cycle indicator for Zurich: a weekly price series from the official quotations as the core, the structure of advertising volume as a second series, dating of turning points after Bry and Boschan, and comparison with the Pfister series. In the meeting of 7 October 2026, Prof. Woitek refocused the work on the price quotations and the comparison with Basel. Jakob Metzler confirmed the summary by email on 12 October 2026 (wording in Appendix B). In PPDAC terms, the concept and the reorientation together form the first iteration of Problem and Plan.

| Element | Concept (September 2026) | Authoritative since 12.10.2026 |
| --- | --- | --- |
| Research question | Zurich business cycles from prices and advertisements | Market integration Zurich–Basel from about 1740 |
| Core series | Kernen price Zurich, weekly | unchanged; plus weekly Basel prices |
| Second series | Advertisement structure by rubric | dropped; rubrics only used to locate the price list |
| Method | Detrending, Bry-Boschan, cross-correlations, VAR | Δln p, RLS with forgetting factor, ρt with bands |
| Comparison | Pfister (1985, 1992), Chambru et al. without newspaper quotations | Basel series; Chambru et al. for validation only |
| Validation | Running numbers, Chambru et al., hand coding, turning points | Chambru et al. and hand coding; benchmark episodes instead of turning points |

## 2.3 Scope

- Not pursued further: advertisement structure as an indicator, dating of turning points, comparison with the Pfister series, vector autoregressive model.

- Still required: the rubric mapping, because it makes the price list findable in every issue. Counting advertisements by rubric comes at no extra cost and, time permitting, can appear descriptively in the essay’s appendix (task 4.09, optional).

- Not used: tithe yields after Pfister (1985), Pfundzoll revenues after Pfister (1992), tithe data by Waser.

## 2.4 Agreed Basis and Open Points

The first six points were confirmed by email on 12 October 2026; the others are own decisions with an entry in the decision log.

| Point | Status | Basis |
| --- | --- | --- |
| Rubric scheme | The course R scripts are authoritative. Rubrics not covered are collected and reported; the scheme is extended as needed. | Email 12.10. (E02) |
| Basel prices | Available, finished, from the Avis project. File, variables, units, week definition and citation still to be clarified. | Email 12.10.; question F1 |
| Pipeline | Own implementation, exclusively in Python. The existing R code serves as a reference; R itself is not installed (E15). | Email 12.10. (E03) |
| Language models (section 3) | Consent has been given. | Email 12.10. (E04) |
| Additional price data for the Master | The weekly Zurich grain series in the format of the price database is sufficient. | Email 12.10. (E05) |
| Essay depth and technical documentation | Open. Requirements will follow by December. | Meeting 7.10.; question F3 |
| Gaps, supplements, change of 1801 | Gaps remain, supplements are merged, from 1801 the last quotation of the week applies. | own decision (E06) |
| Working environment and storage | PyCharm and uv for the pipeline, Quarto CLI for writing only, without executable code; folder structure after TIER with uv.lock and uv run python scripts/run_all.py as the master command (section 6.3). | own decision (E08, E09, E14, E15) |

# 3. Plan

## 3.1 Data Basis

The Zurich data come as one csv file per issue of the Donnstags-Nachrichten and its successor papers. One row corresponds to one advertisement, with issue ID and date, page, full text, type, rubric and a flag for advertisements spanning a page break. Until 1800 the paper appeared weekly, from 1801 twice weekly. All provided data are kept outside the repository under data/input/.

| Source | Period | Role | Storage | Rights |
| --- | --- | --- | --- | --- |
| Donnstags-Nachrichten, Donnstags-Blatt, Zürcherisches Wochenblatt (files DN and ZWB) | 1730 to 1842 | Zurich price series | data/input/zurich/ | Agreement, sections 1 to 5 |
| Weekly Basel prices from the Avis project | 1729 to 1844 | Comparison series | data/input/basel/ | CC BY-NC-SA 4.0; citation Burghartz et al. (2023); not listed in Table 1 of the agreement |
| Price database Chambru et al. (2026), prices_raw_public_use_zh.xlsx | Newspaper quotations 1750 to 1842, median of four months per year | Validation of the extraction, not comparison | data/input/chambru/ | Agreement; citation as in Table 1 (Appendix D) |
| Course R script donnerstagsnachrichten.R | – | Reference for rubrics and merging | reference/ | Course material |

### Particularities of the price lists

- References to the previous week: In the early period the paper sometimes lists only the items that changed. Treatment in section 3.2.

- Ditto marks appear instead of spelled-out goods. Resolved in the price parser (section 4.4).

- Price ranges from the 1820s: the midpoint is used, the range is flagged.

- Units and currency: The unit of quantity changes from Mütt to Malter; the currency remains Gulden, Schilling and Heller throughout. The change of unit is a break within the series (section 3.2).

- OCR: Errors also affect digits and rubric headings. Implausible quotations are flagged using bands per good and decade.

## 3.2 Measurement Concept

- Week axis: Both series are placed on calendar weeks; the week definition is aligned with the Basel series. From 1801 the last Zurich quotation of the week applies. Issues with supplements are merged; missing issues remain as gaps and are not filled.

- Changes instead of levels: The measure is Δln pt = ln pt − ln pt−1. Levels with a common trend would produce correlation even without a market connection. Since the correlation of log changes does not depend on unit and currency, no conversion between Zurich and Basel measures is needed. Across a break within a series, such as the change from Mütt to Malter, the change is set to missing.

- References to the previous week: Items not listed are assigned a change of zero, flagged as carried forward. Illegible or missing quotations remain missing. Since accumulated zeros depress the correlation, every estimate is also computed without carried-forward values.

- Estimation: Δln pZ,t = αt + βt Δln pB,t + εt, recursively with forgetting factor λ. From the same exponentially weighted moments follows ρt = βt σB,t / σZ,t. The effective window is about 1/(1 − λ) weeks.

- Lags: In addition to the contemporaneous correlation, lags of one and two weeks in both directions are reported.

- Uncertainty: Bands for ρt via the Fisher transformation with the effective number of observations, complemented by a block bootstrap with a fixed seed.

- Identification: Zurich and Basel lie in the same climate zone. Common harvest shocks produce price movements in the same direction even without trade. A high correlation is therefore necessary but not sufficient for integration (Federico 2012). Conversely, officially set prices dampen the Zurich series. Both are reported in the essay as limitations. Where units and currencies can be converted, the price spread ln(pZ,t / pB,t) complements the correlation as a second measure.

- Benchmark episodes: the dearth years 1740 and 1741, 1770 and 1771, and 1816 and 1817, in which connectedness or isolation of the markets should show most clearly.

## 3.3 Pre-specified Variants

The variants are fixed before estimation and are all reported. In a lean form they serve the function of a pre-analysis plan. New variants are added only through the decision log and are marked as post hoc.

| Variant | Specification | Purpose | Task |
| --- | --- | --- | --- |
| Base case | λ = 0.98 (about 50 weeks), contemporaneous, with carried-forward values | Main result | 4.03 |
| Without carry-forward | as base case, carried-forward values set to missing | Effect of references to the previous week | 4.03 |
| Shorter memory | λ = 0.96 (about 25 weeks) | Sensitivity | 4.04 |
| Longer memory | λ = 0.99 (about 100 weeks) | Sensitivity | 4.04 |
| Rolling window | 52 weeks, equally weighted | Independence from the weighting scheme | 4.04 |
| Lags | ±1 and ±2 weeks | Travel time of information and goods | 4.04 |
| Price spread (optional) | ln(pZ / pB), if convertible | second measure of integration | 4.05 |
| Further goods (optional) | depending on data quality in both cities | Breadth of the finding | 4.08 |

## 3.4 Lean Data Management Plan

A data management plan is not required. A single page following the SNSF outline nevertheless settles the data questions before the pipeline is built (task 2.05).

| SNSF item | Specification |
| --- | --- |
| 1 Data collection and documentation | Input data as in section 3.1. Produced are the issue register, quotations, analysis dataset and the Zurich series, each as csv in UTF-8 with dates in ISO format. Documented by codebook, check reports, validation log and README. |
| 2 Ethics, legal and security | The signed agreement applies: purpose-bound use (section 1); no disclosure or publication, including derived datasets from which the data can be reconstructed (2); no external services without consent, consent for language models has been given (3); source citations as in Table 1 (4); protected storage and deletion after the end of the project (5). |
| 3 Storage and preservation | Data only locally under data/ on an access-protected device, not in the repository, no cloud without consent. Location of the backup: a peer-to-peer sync folder outside the repository, synchronised only between my own devices (PC, laptop, phone, NAS) without a cloud server in between; every device is access-protected by device encryption and a screen lock (E17). Intermediate and analysis files as csv in UTF-8 with ISO dates, written via src/datafiles.py. Code, Quarto documents and lock file in the private GitHub repository; analysis states tagged at M4 and at submission. After the end of the project all copies are deleted, including backups on all synced devices, unless permission has been granted (task 5.13). |
| 4 Data sharing and reuse | Replication package without raw data, with expected paths and provenance. The Zurich series goes to the supervisors in the format of the price database. Publication, e.g. with a DOI, only with consent under section 2 (question F5). |

The FAIR principles (Wilkinson et al. 2016) serve as the target criteria for the Zurich series:

| Principle | Implementation for the Zurich series |
| --- | --- |
| Findable | Unique ID per quotation from issue ID, date and running number; metadata in the codebook. |
| Accessible | Delivered to the supervisors; access under the agreement. |
| Interoperable | Fields and coding of the price database, csv in UTF-8, ISO dates, units and currency documented. |
| Reusable | Provenance per value, flags (carried forward, range, implausible, break), codebook and citation note. |

## 3.5 Risks

| Risk | Effect | Countermeasure | checked at |
| --- | --- | --- | --- |
| Data quality around 1740 | The research question targets the period with the most references to the previous week and the most OCR errors. | Prototype 1735 to 1745 with pre-specified criteria | M2 |
| Basel series unclear | Week axis, units or coverage do not match. | Ask question F1 immediately, align the week definition early | M2 |
| Set prices | The correlation measures administrative practice rather than the market. | Report phases without change and compare them with ρt | M3, M4 |
| OCR | Wrong digits and headings distort the series. | Plausibility bands, PDCA validation, hand coding | M3 |
| Common shocks | Co-movement driven by weather instead of trade. | Report as a limitation, benchmark episodes, price spread as second measure | M4 |
| Open requirements | Scope and form of essay and documentation will only be fixed in December. | Finish the pipeline independently of the text; Quarto renders PDF, Word or HTML from one source | M4 |
| Working environment | The run depends on PyCharm, on local settings or on an unrecorded Quarto version. | .python-version, uv.lock, Quarto CLI version in the README, run from the command line in a fresh environment, without PyCharm | M5 |

# 4. Data: Pipeline and Validation

The Data phase follows the R4DS cycle (Wickham, Çetinkaya-Rundel and Grolemund 2023): Import, Tidy and Transform in this chapter, Visualize and Model in chapter 5, Communicate in chapter 6. Everything is wrapped by Program: each step is a numbered script with a module in src/, tests in tests/ and a check report in reports/. The step tables also form the outline of the technical documentation, one chapter per step with input, processing, output and checks.

## 4.1 Overview of Steps

| No. | R4DS | Script and module | Output | Check report | Task |
| --- | --- | --- | --- | --- | --- |
| 01 | Import | scripts/01_issues.py src/issues.py | issues.csv, ads.csv, gaps.csv | reports/01_issues.qmd | 2.10 |
| 02 | Tidy | scripts/02_rubrics.py src/rubrics.py | ads_rubrics.csv, price_lists.csv, rubrics_unknown.csv | reports/02_rubrics.qmd | 2.11, 2.12 |
| 03 | Tidy | scripts/03_prices.py src/prices.py | quotations.csv | reports/03_prices.qmd | 3.03, 3.04 |
| 04 | Check (PDCA) | scripts/04_validation.py src/validation.py | validation_*.csv | reports/04_validation.qmd | 3.02, 3.05, 3.07, 3.08 |
| 05 | Transform | scripts/05_weekly_series.py src/weekly_series.py | weekly_series_zh.csv, analysis_zh_bs.csv | reports/05_weekly_series.qmd | 3.06, 4.01 |
| 06 | Model | scripts/06_estimation.py src/rls.py | rho_*.csv, output/tables/, output/figures/ | reports/06_estimation.qmd | 4.02 to 4.05 |
| 07 | Communicate | scripts/07_export.py src/export.py | zurich_price_database.csv | docs/codebook.qmd | 5.03 |

Intermediate results of steps 01 to 04 are stored in data/intermediate/, the results of steps 05 to 07 in data/analysis/. scripts/run_all.py runs the steps in this order and then calls quarto render. Paths, period, λ values, window, lags and the bootstrap seed are set in config.yml.

The check reports compute nothing themselves. Each script writes its figures to output/figures/, its tables to output/tables/ and its key figures to output/values/; the check report in reports/ only embeds them. How pipeline and text work together is set out in section 6.3 under “Working with PyCharm and the Quarto CLI”.

## 4.2 Import: Issue Register

| Input | data/input/zurich/*.csv, one file per issue with issue ID and date, page, full text, type, rubric and continuation flag |
| --- | --- |
| Processing | Reading all files; date and issue ID from the file name; merging advertisements across page breaks following the logic of the R script; resolving hyphens at line ends (rule from the R script, ported with the regex package, since re does not support \p{L}); merging supplements with the main issue; assigning the calendar week |
| Output | issues.csv (one row per issue with week), ads.csv (merged advertisements), gaps.csv (expected but missing issues) |
| Checks | Coverage per year, expected versus available issues; intervals between issues; pytest for date derivation, merging and supplements |
| Status | open, task 2.10 |

## 4.3 Tidy I: Rubric Mapping

| Input | ads.csv; rubric scheme from reference/donnerstagsnachrichten.R |
| --- | --- |
| Processing | Porting the mapping to the scheme of the R scripts; identifying the food price rubric for each period; log of unknown headings |
| Output | ads_rubrics.csv, price_lists.csv (all price lists with issue and date), rubrics_unknown.csv |
| Checks | Row-by-row comparison with the reference output of the R script (zwb_merged, from the supervisors, question F8) on about ten issues from all three titles, every deviation justified; without reference output, comparison via pytest cases with hand-checked advertisements; rubrics not covered reported to the supervisors |
| Status | open, tasks 2.11 and 2.12 |

## 4.4 Tidy II: Price Parser

| Input | price_lists.csv |
| --- | --- |
| Processing | Recognising good (list of goods with spelling variants), unit and amount; resolving ditto marks; midpoint for price ranges; flagging references to the previous week; converting amounts to Heller; plausibility bands per good and decade; optionally extracting hard-to-read lists with a language model and a fixed JSON schema |
| Output | quotations.csv in long format: date, week, issue, good, unit, amount in Heller, flags |
| Checks | pytest on quotations from each period with hand-determined results, including ditto marks and ranges; validation as in section 4.5 |
| Status | open, tasks 3.03 and 3.04 |

## 4.5 Check: Validation

| Input | quotations.csv; hand coding of about 20 issues in data/intermediate/hand_coding/; development/test split in docs/sample.csv (issue IDs only); price database of Chambru et al. |
| --- | --- |
| Processing | Matching by issue, date and good. Precision is the share of extracted quotations whose good, unit and amount match the hand coding; recall the share of hand-coded quotations that were extracted correctly; F1 the harmonic mean. Per PDCA iteration on the development set, once at the end on the test set. Against Chambru et al.: share of identical values and mean deviation |
| Output | validation_*.csv, reports/04_validation.qmd, entries in docs/validation_log.qmd |
| Checks | Coding rules fixed before coding; test set used only once; stability criterion as in section 4.7; large deviations from Chambru et al. explained individually (parser, OCR or source) |
| Status | open, tasks 3.02, 3.05, 3.07 and 3.08 |

## 4.6 Transform: Weekly Series

| Input | quotations.csv; Basel series from data/input/basel/ |
| --- | --- |
| Processing | Weekly series per good as in section 3.2: from 1801 the last quotation of the week, carry-forward flagged, break from Mütt to Malter as missing change, gaps remain; computing Δln p; merging with Basel on the common week axis |
| Output | data/analysis/weekly_series_zh.csv, data/analysis/analysis_zh_bs.csv |
| Checks | Coverage per year and good; phases without any price change; number of weeks with a quotation in both cities per year; diagnostic figures as in section 5.2 |
| Status | open, tasks 3.06 and 4.01 |

## 4.7 PDCA Micro-cycle for Extraction

Price extraction does not succeed in a single pass. It is improved in explicit Plan-Do-Check-Act cycles after Shewhart (1939) until the metrics are stable. The prerequisite is the hand coding (task 3.02), because without a reference there is no check.

- Plan: Define an extraction rule for one period or special case, such as ditto marks or references to the previous week. Only one well-defined change per iteration, so that its effect remains attributable.

- Do: Run the parser over the period, commit the state.

- Check: Compute precision, recall and F1 on the development set and the comparison with Chambru et al. via scripts/04_validation.py, never by hand.

- Act: Adopt or discard the rule, log deviations, plan the next iteration.

Stopping rule: Extraction counts as stable when the F1 score on the development set rises by less than one percentage point in two consecutive iterations and the target value for M3 is reached (section 7.2). The parser is then frozen and measured once on the test set. Error examples are cited in the log only by issue ID and position, without full text.

Template for docs/validation_log.qmd:

| No. | Date | Period or special case | Plan: rule change | Check: P / R / F1 before → after | Act: decision | Commit |
| --- | --- | --- | --- | --- | --- | --- |
| V01 | dd.mm. | 1740s, references to previous week | Flag reference to previous week as carried forward | 0.00 / 0.00 / 0.00 → … | adopted | abc1234 |
| V02 |  |  |  |  |  |  |
| V03 |  |  |  |  |  |  |

# 5. Analysis: Estimation and Presentation

## 5.1 Model: RLS Estimation

| Input | data/analysis/analysis_zh_bs.csv; config.yml with λ values, window, lags and seed |
| --- | --- |
| Processing | Recursive estimation of αt and βt with forgetting factor; ρt from the exponentially weighted moments; all variants as in section 3.3; bands via the Fisher transformation and block bootstrap |
| Output | data/analysis/rho_*.csv, tables in output/tables/, figures in output/figures/, reports/06_estimation.qmd |
| Checks | With λ = 1 the last value equals the least squares estimate over all weeks; comparison with RecursiveLS from statsmodels; simulated series with known, changing correlation; burn-in period fixed during which ρt is not interpreted; fixed seed |
| Status | open, tasks 4.02 to 4.05 |

## 5.2 Visualize: Figures and Tables

Every figure and table is produced by a script as a file and carries its ID as file name and as label for cross-references in Quarto. Figures are saved as PNG at 300 dpi so that PDF and Word render them identically; tables additionally as Markdown with caption and label, embedded via {{< include >}}. The list also forms the README section “List of tables and figures”.

| ID | Contents | Use | produced by |
| --- | --- | --- | --- |
| fig-coverage | Coverage per year and good | Diagnostics, essay | 05 |
| fig-gaps | Gaps and phases without price change | Diagnostics | 05 |
| fig-plausibility | Quotations with plausibility bands | Diagnostics | 03 |
| fig-prices | Kernen prices Zurich and Basel | Essay | 05 |
| fig-rho | ρt with band, base case | Essay, main result | 06 |
| fig-sensitivity | ρt for λ = 0.96, 0.98, 0.99 and 52 weeks | Essay | 06 |
| fig-benchmarks | Benchmark episodes 1740/41, 1770/71, 1816/17 | Essay | 06 |
| tbl-data | Data coverage | Essay | 05 |
| tbl-validation | Precision, recall, F1; comparison with Chambru et al. | Essay | 04 |
| tbl-sensitivity | Results of the variants from section 3.3 | Essay | 06 |

## 5.3 Freezing the Results

- M4, Wed 16.12.2026: The core results (Kernen, base case and all must variants, benchmark episodes) are frozen with the tag m4-core-results. After that the core receives only bug fixes, each with an entry in the decision log.

- Additions until Wed 23.12.2026: Further goods and the advertisement count are added as separate results without changing the core. Figures and tables are finalised; the state receives the tag analysis-final.

- From then on: The essay reads numbers exclusively via {{< var >}} from _variables.yml, which scripts/run_all.py writes from the result files of this state.

# 6. Conclusion: Submission and Replication Package

## 6.1 Parts of the Submission

| Part | Form | Source in the project | Assessment | Tasks |
| --- | --- | --- | --- | --- |
| Essay (8 pages) | PDF from essay/essay.qmd, Word from the same source if needed | essay/ | Application (60 %) | 5.01, 5.05, 5.06, 5.08 |
| Replication package | Repository state with tag submission, without raw data | whole project | Application (60 %) | 5.02, 5.04, 5.09 |
| Zurich series with codebook | csv in the format of the price database, codebook as PDF | data/analysis/, docs/codebook.qmd | Application; condition for the Master | 5.03 |
| Contribution to the joint data documentation | as per question F2 | docs/data_documentation.qmd | Data documentation (20 %) | 3.09, 5.07 |
| Declaration of independent work and AI tools | if required | docs/language_models.qmd | Formalities | 5.08 |

## 6.2 Essay: Outline along PPDAC

The outline follows the PPDAC phases. The page budget is provisional; the requirements to follow by December are authoritative (task 4.06). References and appendix will probably not count towards the length; this is clarified with question F3.

| Section | PPDAC | Contents | Pages |
| --- | --- | --- | --- |
| Introduction and research question | Problem | Research question, positioning in the literature on market integration (Federico 2012) | 0.75 |
| Source and group work | Problem, Plan | Donnstags-Nachrichten; pipeline, annotation and text structuring from the group phase | 1.0 |
| Construction and validation of the series | Data | Rubrics, parser, special cases, measurement quality | 1.75 |
| Method | Plan, Analysis | Δln p, RLS, ρt, bands, variants | 1.0 |
| Results | Analysis | ρt over time, sensitivity, benchmark episodes | 2.25 |
| Limitations | Conclusion | early period, set prices, OCR, common shocks | 0.75 |
| Conclusion | Conclusion | Answer to the research question | 0.5 |
| Total |  |  | 8.0 |

## 6.3 Folder Structure after TIER, Implemented with Quarto and uv

The structure adopts the logic of the TIER Protocol 4.0: fixed folders, one master command, relative paths and input data that are not part of the package. Instead of requirements.txt, uv.lock pins the package versions. The master command is uv run python scripts/run_all.py: the script runs steps 01 to 07, writes _variables.yml and finally calls quarto render (decision E14; replaces the pre-render from E09).

| Folder or file | Contents | Repository | Package |
| --- | --- | --- | --- |
| README.md | Description after the Template README (section 6.4) | yes | yes |
| _quarto.yml | Project configuration: folders to render reports/, essay/, docs/; output to _output/; formats Typst PDF and Word; bibliography. No pre-render, no executable code cells | yes | yes |
| _variables.yml | Key figures from output/values/, merged by scripts/run_all.py; used in the text via {{< var key >}} | no | no, generated |
| config.yml | relative paths, period, λ values, window, lags, seed | yes | yes |
| pyproject.toml, uv.lock, .python-version | Python version and pinned package versions | yes | yes |
| data/input/ | Raw data in zurich/, basel/, chambru/ | no | no, paths in the README |
| data/intermediate/ | Intermediate results of scripts 01 to 04, hand coding | no | no |
| data/analysis/ | Analysis dataset, ρt, Zurich series | no | no; Zurich series separately |
| src/, tests/ | Modules per step, tests with pytest | yes | yes |
| scripts/01_… to 07_… | one script per pipeline step, numbered in order of execution | yes | yes |
| scripts/run_all.py | Master: runs 01 to 07, stops on errors, logs run times, writes _variables.yml and calls quarto render; --no-render for data runs only | yes | yes |
| reports/ | Check report per step (.qmd without code), embeds the step’s figures, tables and key figures | yes | yes |
| essay/ | essay.qmd, references.bib, CSL style | yes | yes |
| docs/ | Codebook, validation log, coding rules, sample, data documentation, group phase, language models, provenance of the input data (provenance.yaml) | yes | yes |
| output/figures/, output/tables/, output/values/ | Figures (PNG, 300 dpi), tables (csv and Markdown), key figures per step (yml) | no | no, generated |
| _output/ | rendered reports and essay; may contain data extracts | no | no |
| reference/ | Course R script, unchanged, text reference only; R is not executed (E15) | yes | no |
| .run/ | PyCharm run configurations (see below) | yes | yes |
| .idea/ | local PyCharm settings | no | no |

Rendered reports, like the data, stay outside the repository and are not published with quarto publish or any other service (sections 2 and 3). PyCharm is not needed for reproduction; the run works from the command line alone.

### Working with PyCharm and the Quarto CLI

Since 26 October 2026 the pipeline has been developed in PyCharm; Quarto serves only as a typesetting tool (E14). All computation happens in Python; Quarto only reads finished files. Code and text work thus stay separate, and an error in the text cannot change a result.

| Element | Specification |
| --- | --- |
| Roles | PyCharm for pipeline, tests and data inspection. The Quarto CLI only typesets check reports, essay, codebook and data documentation. The .qmd files contain no executable code cells; Quarto therefore needs neither Jupyter nor a Python engine. |
| Hand-over to the text | The pipeline writes figures to output/figures/ (file name equal to the ID from section 5.2), tables as Markdown to output/tables/ and key figures per step to output/values/NN.yml; run_all.py merges the key figures under the keys s01 to s07 into _variables.yml. In the text: ![Title](../output/figures/fig-rho.png){#fig-rho}, {{< include ../output/tables/tbl-data.md >}} and {{< var s06.rho_1740 >}}. Nothing is transferred by hand. |
| Interpreter | .venv from uv as the project interpreter in PyCharm; new packages only with uv add, never via PyCharm’s package manager, so that uv.lock stays complete. |
| .qmd in PyCharm | *.qmd assigned to the Markdown file type under Settings → Editor → File Types. PyCharm offers only syntax highlighting for Quarto; its Markdown preview does not understand citations, cross-references and shortcodes and is not used. |
| Preview | In the PyCharm terminal quarto preview essay/essay.qmd --to typst; Quarto re-renders on every save. After a pipeline run, save the .qmd once so that new figures and values appear. |
| Run configurations | As project files in .run/, versioned: “Pipeline” (scripts/run_all.py --no-render), “Full run” (scripts/run_all.py), “Tests” (pytest over tests/), “Essay preview” (shell script with the preview command). |
| Data inspection | PyCharm’s DataFrame view in the Python console or debugger; replaces Positron’s Data Explorer. No screenshots of it in cards or issues (section 7.4). |
| Coding assistants | AI assistants in PyCharm can send code and context to the provider: use them only within the consent under section 3 and log them as in Q5. |
| Reproduction | PyCharm is not needed: uv sync --locked, then uv run python scripts/run_all.py from the command line, with the Quarto CLI in the version stated in the README. |

## 6.4 README after the Template README

The Template README of the Social Science Data Editors (2020) defines the sections. The table sets out where the information comes from.

| Section | Content in the project | from task |
| --- | --- | --- |
| Overview | What the package produces (analysis data, figures, tables, essay) and how long a full run takes | 5.04 |
| Data Availability and Provenance | Provenance of each source, access via the supervisors, terms of the agreement; note that the raw data are not included under section 2; citations as in Table 1 | 2.04 |
| Dataset list | every input file with expected path, source and format | 2.04 |
| Computational requirements | uv, Python version, packages from uv.lock, Quarto CLI version (PDF via Typst), run time, hardware; neither Jupyter nor R required; steps using a language model with model, version, parameters and cost | 2.02, 2.03, Q5 |
| Description of programs | Scripts and modules as in section 4.1 | 4.1 |
| Instructions to replicators | Clone the repository; place raw data at the paths; uv sync --locked; uv run python scripts/run_all.py; results in output/ and _output/ | 5.04 |
| List of tables and figures | ID, file and generating script as in section 5.2 | 4.10 |
| References | Data sources and literature | 5.06 |

The AEA revised its Data and Code Availability Policy in 2024. The Template README remains the reference; the current version is checked before submission, and question F3 clarifies whether README and check reports in this form are accepted as technical documentation (task 4.06).

## 6.5 Checking the Package

The run in a fresh environment is gate M5 (Fri 15.1.2027) and is repeated with the submission state on Wed 27.1.2027:

- Fresh clone of the repository into an empty folder, without PyCharm.

- Place raw data at the paths described in the README.

- uv sync --locked creates the environment from uv.lock.

- uv run python scripts/run_all.py from the command line through to figures, tables and essay; measure the run time; check the Quarto CLI version (quarto --version) against the README.

- Compare the result files with the state analysis-final; they must match.

- The essay renders without warnings on cross-references and citations.

- The package contains no raw data and no file from which the provided data can be reconstructed; check rendered reports for data extracts.

# 7. Project Management

Project management follows the logic of work packages, milestones and Gantt chart customary in research funding, in a scaled-down form. The milestones take on the role of the IPERKA phase “Decide”: at every gate, pre-specified check questions determine whether work continues as planned.

## 7.1 Work Packages and Milestones

| Work package | Period | Result | Milestone | Status |
| --- | --- | --- | --- | --- |
| WP0 Group phase | 7.7. to 18.8.2026 | Seven meetings attended, group assignments submitted | – | done |
| WP1 Concept and reorientation | 19.8. to 15.10.2026 | Concept, confirmed direction, planning framework, this documentation | M1 Mon 12.10. (reached) | done |
| WP2 Data basis and prototype | 14.10. to 1.11.2026 | Project running after TIER, issue register, rubric mapping, prototype 1735 to 1745 | M2 Sun 1.11. | current |
| WP3 Price parser and validation | 2.11. to 29.11.2026 | Zurich weekly series 1730 to 1842 with documented measurement quality | M3 Sun 29.11. | open |
| WP4 Estimation | 30.11. to 23.12.2026, buffer until 3.1.2027 | Core results frozen, figures and tables finished, requirements obtained | M4 Wed 16.12. | open |
| WP5 Essay and replication package | 4.1. to 29.1.2027 | Essay, checked package, Zurich series, data documentation submitted | M5 Fri 15.1.; submission Fri 29.1. | open |

Submission is set for Friday, 29 January 2027; the learning unit ends on 31 January 2027. M2 is the most important decision point, because the research question targets 1740, where data quality is weakest.

## 7.2 Gates: Check Questions and Decisions

The target values are a proposal. They are confirmed or adjusted before each gate, for M2 by Thu 22.10. in task 2.08, and not changed afterwards. This way the result does not decide the criterion.

| Gate | Check questions with target value | Possible decisions |
| --- | --- | --- |
| M2 Sun 1.11.2026 Does the series hold up around 1740? | 1. Coverage: at least 70 % of the weeks 1735 to 1745 with a usable Kernen quotation in both cities. 2. Accuracy: at most 5 % deviating quotations in the hand check of two years. 3. Carry-forward: at most half of the Zurich weekly values carried forward, so that the variant without carry-forward remains estimable. 4. Informativeness (judgement): the band of ρt is narrow enough to distinguish weak from strong integration. | Proceed: all points met. Adjust: point 1 or 3 narrowly missed; later start, monthly frequency or another grain, agreed with the supervisors (question F7). Return to Problem: research question cannot be answered for 1740; adjust the question and have it confirmed in writing. |
| M3 Sun 29.11.2026 Is the Kernen series complete and validated? | 1. Period 1730 to 1842 fully processed, gaps documented in gaps.csv. 2. F1 for Kernen quotations on the test set at least 0.95. 3. Stability reached as in section 4.7. 4. Comparison with Chambru et al. reported, large deviations explained. | Proceed with WP4. Proceed with restriction: flag periods with weak measurement quality and exclude them in a variant. Rework: targeted, by Sun 6.12. at the latest, at the expense of the buffer. |
| M4 Wed 16.12.2026 Are the core results in place? | 1. Base case and all must variants from section 3.3 computed and stored. 2. RLS tests passed (λ = 1 against least squares, RecursiveLS, simulation). 3. Benchmark episodes evaluated. 4. Requirements for essay and documentation obtained, or follow-up noted. | Freeze with tag m4-core-results. Freeze with open variant: report the missing variant as a limitation in the essay. Do not freeze only in case of an error in the core; correction by Wed 23.12. |
| M5 Fri 15.1.2027 Does the package run in a fresh environment? | 1. uv sync --locked and uv run python scripts/run_all.py run through without intervention. 2. Result files match the state analysis-final. 3. README complete as in section 6.4. 4. No raw data and no reconstructable data in the package. | Release: only text work until submission. Rework by Wed 20.1., repeat the run; it must succeed at the final run on Wed 27.1. at the latest. |

At every gate, the decision with the answers to the check questions is entered in the decision log, tables 1.3 and 10.2 are updated, a Gibbs entry is written and the cards of the next work package are created.

## 7.3 Gantt Overview

| Work package | October |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 |
| WP2 Data basis and prototype |  |  | M2 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP3 Parser and validation |  |  |  |  |  |  | M3 |  |  |  |  |  |  |  |  |  |
| WP4 Estimation |  |  |  |  |  |  |  |  |  | M4 |  | B |  |  |  |  |
| WP5 Essay and package |  |  |  |  |  |  |  |  |  |  |  |  |  | M5 |  | S |
| Obtain requirements (4.06) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Data documentation (3.09) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Reflection (Gibbs) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Blue: work package. Dark: milestone (M) and submission (S). Light: buffer (B) or ongoing task. Green: Gibbs entry. Calendar weeks: CW 42 = 12 to 18 October 2026, CW 53 = 28 December 2026 to 3 January 2027, CW 4 = 25 to 31 January 2027.

## 7.4 Kanban Board in GitHub Projects

The board is a GitHub Project attached to the private repository and steers day-to-day work. The scope is set by the checklist in chapter 10; the board mirrors it.

| Element | Specification |
| --- | --- |
| Columns | Backlog · In Progress · Waiting for Feedback · Done |
| Limit | At most two cards in “In Progress” at the same time. |
| Card | One card per checklist task, title with ID, e.g. “2.10 Build issue register”. Sub-steps as a task list in the card. |
| Fields | Work package, due date, must or optional; GitHub milestones M2 to M5 with date. |
| Waiting for Feedback | All cards that depend on a question to the supervisors, with a reference to the question in section 9.2. |
| Linking | Commit messages state ID and issue number, e.g. “2.10 Gap list per year (#12)”. |
| Creation | Cards of a work package are created at the preceding gate, for WP2 immediately (task 2.06). |
| Data protection | No data extracts, no screenshots of data and no rendered check reports in cards or issues (sections 2 and 3). |

## 7.5 Weekly Rhythm

Every Sunday, about 30 minutes (task Q4):

- Reconcile board and checklist, tick off what is done.

- Check due dates; adjust postponed dates and record the consequences for the next milestone.

- Update decision log and question list, send questions in bundles.

- Pull the coming week’s tasks from the backlog, respecting the limit of two.

# 8. Reflection after Gibbs

## 8.1 Procedure

After each milestone a short entry of about half a page is written along the six steps of the Reflective Cycle (Gibbs 1988), at the latest three days after the gate. The action plan is moved into the backlog as cards. At the end, the entries yield a reflection section at no extra cost, if the requirements provide for one.

| Step | Research question |
| --- | --- |
| Description | What happened? |
| Feelings | How did I experience the situation, what did I think? |
| Evaluation | What was good, what was difficult? |
| Analysis | Why did it turn out this way? |
| Conclusion | What do I take away from it? |
| Action Plan | What will I do differently next time, concretely and with a card? |

## 8.2 Entry M1: Reorientation (7 to 12 October 2026)

Prepared from the planning framework; to be reviewed and completed in task 2.07.

| Step | Entry |
| --- | --- |
| Description | Meeting with Prof. Woitek on 7 October 2026. Shift from the business cycle indicator based on price series and advertisement structure to Zurich–Basel market integration based on the official price quotations. Summary by email, confirmed by Jakob Metzler on 12 October. |
| Feelings | to be filled in personally: How did I experience the meeting and the change of course? |
| Evaluation | Good: clear, measurable research question; the Basel series is available; the direction is confirmed in writing. Difficult: parts of the concept can no longer be used, and the research question targets the period with the weakest data quality. |
| Analysis | The concept was broad. The supervisors put the emphasis on prices, and the Basel data from the Avis project make the city comparison possible without additional data collection. |
| Conclusion | Have the direction confirmed in writing early. A narrow focus makes a robust measurement easier. |
| Action Plan | Define decision points with criteria in advance (task 2.08). Prototype before expanding the pipeline (2.13). Ask questions in bundles (Q3). |

## 8.3 Entries M2 to M5 and Conclusion

### Entry M2: Prototype and decision on the early period

by Wed 4.11.2026

| Step | Entry |
| --- | --- |
| Description |  |
| Feelings |  |
| Evaluation |  |
| Analysis |  |
| Conclusion |  |
| Action Plan |  |

### Entry M3: Kernen series and measurement quality

by Wed 2.12.2026

| Step | Entry |
| --- | --- |
| Description |  |
| Feelings |  |
| Evaluation |  |
| Analysis |  |
| Conclusion |  |
| Action Plan |  |

### Entry M4: Core results

by Sat 19.12.2026

| Step | Entry |
| --- | --- |
| Description |  |
| Feelings |  |
| Evaluation |  |
| Analysis |  |
| Conclusion |  |
| Action Plan |  |

### Entry M5: Replication package

by Mon 18.1.2027

| Step | Entry |
| --- | --- |
| Description |  |
| Feelings |  |
| Evaluation |  |
| Analysis |  |
| Conclusion |  |
| Action Plan |  |

### Final entry: the project as a whole

by Sun 31.1.2027

| Step | Entry |
| --- | --- |
| Description |  |
| Feelings |  |
| Evaluation |  |
| Analysis |  |
| Conclusion |  |
| Action Plan |  |

# 9. Decision Log and Open Questions

## 9.1 Decision Log

Every deviation from the plan and every piece of feedback from the supervisors is recorded here with date and basis (task Q1). Entries are not deleted but superseded by new ones.

| No. | Date | Decision | Rationale | Basis |
| --- | --- | --- | --- | --- |
| E01 | 07.10.2026 | Reorientation: Zurich–Basel market integration via the RLS correlation of weekly price changes, base price Kernen | Goal set by Prof. Woitek; Basel data available | Meeting 7.10., confirmed 12.10. |
| E02 | 12.10.2026 | The rubric scheme of the R scripts is authoritative; missing rubrics are reported | Consistency with the course | Email 12.10. |
| E03 | 12.10.2026 | Pipeline exclusively in Python, R code as reference | own implementation | Email 12.10. |
| E04 | 12.10.2026 | Use of language models under section 3 permitted | Consent has been given | Email 12.10. |
| E05 | 12.10.2026 | The weekly Zurich grain series in the format of the price database meets the condition for the Master | no further requirements | Email 12.10. |
| E06 | 14.10.2026 | Gaps remain, supplements are merged, from 1801 the last quotation of the week applies, breaks as missing change | no filling without information; uniform weekly frequency | own decision |
| E07 | 14.10.2026 | Planning framework: PPDAC, R4DS with PDCA, TIER with Template README and DMP, work packages with Gantt and Kanban, Gibbs | established standard per level | Planning framework |
| E08 | 15.10.2026 | Working environment Positron, uv and Quarto | reproducible environment; essay and documentation from one source | own decision |
| E09 | 15.10.2026 | Folder structure after TIER, implemented with Quarto and uv: uv.lock instead of requirements.txt, uv run quarto render as master command via scripts/run_all.py | links TIER with E08 | own decision |
| E10 | 15.10.2026 | Milestones M2 Sun 1.11., M3 Sun 29.11., M4 Wed 16.12., M5 Fri 15.1.; submission Fri 29.1.2027 | Rhythm of the framework; buffer before the deadline of 31.1. | own decision |
| E11 | 15.10.2026 | Management via GitHub Projects; the checklist in chapter 10 remains authoritative for scope | Cards can be linked to commits | own decision |
| E12 | 15.10.2026 | Hand coding before the PDCA iterations, split into development and test sets | the check needs a reference; the test set stays untouched | own decision |
| E13 | 15.10.2026 | New documentation along the planning framework, checklist by work package with new IDs; the earlier documentation becomes an archive | one authoritative source | own decision |
| E14 | 26.10.2026 | Working environment PyCharm instead of Positron; Quarto CLI only as a typesetting tool without executable code; key figures via _variables.yml, figures and tables as files; master command uv run python scripts/run_all.py instead of pre-render. Supersedes E08 and the master command from E09 | Computing and writing separated; Quarto renders without a Jupyter kernel; a single master command remains (TIER) | own decision |
| E15 | 26.10.2026 | R is not installed; the R script remains a text reference in reference/. Port to Python with the help of a language model (Q5); comparison in 2.12 via the supervisors’ reference output (F8), otherwise via pytest cases | one language in the environment; reproduction without R | own decision |
| E16 | 29.10.2026 | Task 2.04 gets the standalone script scripts/inventory.py, not called by scripts/run_all.py: files and issues per year, header check, empty files. Provenance is kept by hand in docs/provenance.yaml; the script checks it and writes the README tables. | 2.04 checks the input data once and is not a pipeline step; provenance (source, date obtained, access) cannot be derived from the files | own decision |
| E17 | 29.10.2026 | Task 2.05: backup of data/ in a peer-to-peer sync folder between own devices (PC, laptop, phone, NAS), no cloud server; every device access-protected; deletion in 5.13 covers all devices. Intermediate results as csv, UTF-8, ISO dates via src/datafiles.py | Agreement sections 3 and 5: no external cloud platform, protection against unauthorised access; one format for all steps | own decision |
| E18 |  |  |  |  |

## 9.2 Open Questions for the Supervisors

Questions are collected here and sent in bundles (task Q3). If a card depends on a question, it sits in the column “Waiting for Feedback”.

| No. | Question | to | needed by | Status |
| --- | --- | --- | --- | --- |
| F1 | Basel series: file, variables, units, currency, week definition, citation | Jakob Metzler | Sun 18.10. (2.04) | partly answered from the data (29.10.): file tables/prices.csv, variables, Kernen in Sack, citation via Zenodo; still open: currency, week definition (published or created), meaning of type fixed |
| F2 | Contribution to the joint data documentation: format, storage location, scope, due date | Jakob Metzler | Fri 6.11. (3.01) | open |
| F3 | Requirements for essay and technical documentation: scope, format, submission channel, package contents; are a README after the Template README and Quarto check reports accepted? | Prof. Woitek, Jakob Metzler | Fri 11.12. (4.06) | announced for December |
| F4 | Does the comparison with Basel cover the required comparison with an alternative indicator? | Prof. Woitek, Jakob Metzler | Fri 11.12. (4.06) | open |
| F5 | May the Zurich series be published under section 2, e.g. with a DOI? | Prof. Woitek | Fri 11.12. (4.06) | Optional |
| F6 | Rubrics not covered (list from 2.12) | Prof. Woitek, Jakob Metzler | Tue 27.10. (2.12) | produced in 2.12 |
| F7 | Confirmation of a fallback variant if M2 turns out negative | Prof. Woitek, Jakob Metzler | after Sun 1.11. (2.14) | only if needed |
| F8 | Reference output of the R script (zwb_merged) as csv for about ten issues from all three titles, to check the Python port | Jakob Metzler | Tue 27.10. (2.12) | open |
| F9 | Zurich issue files (DN, ZWB) and course R script: citation (both not listed in Table 1 of the agreement, Appendix D), provider and version or date of the export | Jakob Metzler | Fri 6.11. (2.04) | open |

# 10. Checklist from Project Start to Submission

The checklist breaks the plan down into individual tasks and is authoritative for scope; the board in GitHub Projects mirrors it. It is organised by work package, each ending with a gate. Tasks before 15 October 2026 are marked as done. The boxes can be ticked in Word with a click.

## 10.1 Legend

| Symbol | Meaning |
| --- | --- |
| ☐ / ☒ | open / done |
| 2.10 | ID made of work package and running number; the same on the card in GitHub Projects and in commit messages. Q1 to Q8 are ongoing tasks. |
| formerly C5 | ID in the earlier documentation, for orientation during the transition. |
| Gate M2 | Milestone with decision based on the check questions in section 7.2, highlighted in green. |
| Must / Optional | Must: required for submission or a prerequisite for a later step. Optional: addition if time remains; if dropped, the submission remains complete. |
| Participation, data documentation, application | Part of the assessment: active participation (20 %), individual input to the joint data documentation (20 %), application with indicator, comparison, essay and replication package (60 %). |
| Formalities | Prerequisite without its own share of the grade. |
| Import, Tidy, Check, Transform, Model, Visualize, Communicate | Step in the R4DS cycle with reference to the section; Plan, Decide, Control, Management and Reflection denote a PPDAC phase or an element of the framework. |
| Due | Target date. If a task slips, the date is adjusted, not deleted (Q4). |
| Result | Evidence by which the task counts as done. |

## 10.2 Overview of Work Packages

| Work package | Period | Result at the end | Gate | Status |
| --- | --- | --- | --- | --- |
| WP0 Group phase | 7.7. to 18.8.2026 | seven meetings, group assignments submitted | – | done |
| WP1 Concept and reorientation | 19.8. to 15.10.2026 | Direction confirmed, framework, documentation | M1 (1.04) | done |
| WP2 Data basis and prototype | 14.10. to 1.11.2026 | Project running, import and rubrics, prototype with decision | M2 (2.14) | current |
| WP3 Price parser and validation | 2.11. to 29.11.2026 | Zurich weekly series 1730 to 1842, validated | M3 (3.11) | open |
| WP4 Estimation | 30.11.2026 to 3.1.2027 | Core results frozen, figures and tables finished | M4 (4.07) | open |
| WP5 Essay and replication package | 4.1. to 29.1.2027 | Package checked, submission on Fri 29.1.2027 | M5 (5.04) | open |
| Q Ongoing tasks | whole duration | Log, board, logs, reflection | – | ongoing |

## 10.3 Coverage of the Assessment

Every part of the assessment from the registration for the learning unit is assigned to at least one task. Following the direction of 12 October, the Basel series provides the comparison with an alternative indicator; 4.06 has this confirmed.

| Part of the assessment | Weight | Tasks |
| --- | --- | --- |
| Active participation in the joint sessions | 20 % | 0.02 to 0.08, 1.03 (done); 2.09, 3.10, Q3 |
| Individual input to the joint data documentation | 20 % | 3.01, 3.09, 5.07; Q1, Q6 |
| Application: indicator based on own dataset | 60 % in total | 2.10 to 2.14, 3.02 to 3.08, 4.01 to 4.05, 4.07 |
| Application: comparison with alternative indicator (Basel series) | within 60 % | 2.04, 2.13, 4.01 to 4.05, 4.08; confirmation in 4.06 |
| Application: essay (8 pages) | within 60 % | 2.09, 5.01, 5.05, 5.06, 5.08 |
| Application: replication package | within 60 % | 2.01 to 2.03, 5.02, 5.04, 5.09; Q2, Q5 |
| Additional price data for credit in the Master | Condition | 3.06, 5.03 |

## 10.4 Ongoing Tasks

These tasks run across all work packages and are checked in the weekly review.

☐	Q1	Maintain the decision log

weekly and at every gate · Must · Data documentation, application · Management

☐	enter every deviation from chapters 3 to 6 with date, rationale and basis in section 9.1, only then change the plan

☐	enter feedback from the supervisors and update section 2.4

☐	record decisions at gates with the answers to the check questions from section 7.2

Result: Section 9.1 is up to date.

☐	Q2	Back up code, keep data out of the repository

ongoing · Must · Application · Program

☐	commit regularly: src, tests, scripts, reports, essay, docs, .run, _quarto.yml, config.yml, pyproject.toml, uv.lock, .python-version

☐	commit message with ID and issue number, e.g. “2.10 Gap list per year (#12)”

☐	data/, output/, _output/, _variables.yml, .quarto/, .venv/ and .idea/ stay outside the repository (.gitignore)

☐	no notebooks: code in .py (PyCharm), text in .qmd without code cells

☐	publish nothing with quarto publish, Quarto Pub, GitHub Pages or similar services

☐	Q3	Collect questions for the supervisors and send them in bundles

ongoing · Optional · Participation · Management

☐	collect questions in section 9.2 instead of mailing them individually

☐	move affected cards to the column “Waiting for Feedback”

☐	record answers in 9.2 and in the decision log (Q1)

☐	Q4	Weekly review on Sunday

weekly (Sun) · Must · Formalities · Management

☐	reconcile board and checklist, tick off what is done

☐	adjust postponed dates, check consequences for later tasks and the next milestone

☐	at most two cards in “In Progress”; pull the week’s tasks from the backlog

☐	Q5	Log the use of language models

ongoing · Must · Application · Program

☐	per run in docs/language_models.qmd: model, version, purpose, prompt version, parameters, cost

☐	Coding assistants in PyCharm (JetBrains AI Assistant or others), if used: record the purpose; they can send code and context to the provider, so only within the consent under section 3

☐	Port of the R script to Python with a language model: record model, date, parts ported and the check in 2.12 (E15)

☐	Basis for the README (5.02) and any declaration on AI tools (5.08)

☐	Q6	Log PDCA iterations

per iteration · Must · Application, data documentation · Check (PDCA)

☐	entry in docs/validation_log.qmd following the template in section 4.7

☐	take metrics before and after from scripts/04_validation.py, never by hand

☐	Q7	Gibbs entry after every milestone

at the latest three days after the gate · Must · Application · Reflection

☐	about half a page in section 8.3

☐	move the action plan into the backlog as cards

☐	Q8	Keep this documentation up to date

at every gate · Must · Formalities · Management

☐	fill in the “Status” row of the step tables in chapters 4 and 5

☐	bring tables 1.3 and 10.2 up to date

☐	enter version, date and change in Appendix C; update “Next gate” in the project profile

## 10.5 WP0 Group Phase (7 July to 18 August 2026)

Completed. The group work is covered in the essay; the material for it is secured by 2.09.

☒	0.01	Registration for the Individual Learning Unit completed: 6 ECTS with Prof. Woitek, 1 August 2026 to 31 January 2027, credit in the Master (elective area OEC)

done · Formalities · formerly A1

☒	0.02	Meeting 1, 7 July: introduction; read one complete issue, looked at the Avisblatt project

done · Participation · formerly A2

☒	0.03	Meeting 2, 17 July: pipeline and text line recognition; corrected 20 text columns in Label Studio, export sent to Jakob Metzler by 23 July

done · Participation · formerly A3

☒	0.04	Meeting 3, 20 July: text structuring with language models; prompt developed and tested against the gold standard

done · Participation · formerly A4

☒	0.05	Meeting 4, 28 July: text as data

done · Participation · formerly A5

☒	0.06	Meeting 5, 4 August: business cycle analysis; Python code translated to R with AI

done · Participation · formerly A6

☒	0.07	Meeting 6, 11 August: impulse response functions, loading the data in R

done · Participation · formerly A7

☒	0.08	Meeting 7, 18 August: turning points after Bry and Boschan, dictionaries, classification with language models

done · Participation · formerly A8

## 10.6 WP1 Concept and Reorientation (19 August to 15 October 2026)

Completed with M1 on 12 October 2026. The result is chapters 2 and 3 of this documentation.

☒	1.01	Concept by 18 September, 24:00, to Prof. Woitek and Jakob Metzler

done · Application · Problem, Plan · formerly B1

☒	1.02	Research data use agreement signed and sent with the concept

done · Formalities · formerly B2

☒	1.03	Office hour with Prof. Woitek booked and held on 7 October

done · Participation · formerly B3

☒	1.04	Gate M1: summary by email, confirmed by Jakob Metzler on 12 October

done · Formalities · Decide · formerly B4

☒	1.05	Documentation switched to the new direction (as of 14 October)

done · Application · formerly B5

☒	1.06	Registration and credit checked: receipt at the Dean’s Office confirmed, elective area OEC recorded

done · Formalities · formerly C2

☒	1.07	Planning framework created (14 October)

done · Application · Plan

☒	1.08	Documentation rebuilt along the planning framework (this document, 15 October)

done · Application · Management

## 10.7 WP2 Data Basis and Prototype (14 October to 1 November 2026)

The goal is a working project after TIER with uv, PyCharm and the Quarto CLI, the core of the pipeline up to the rubric mapping, and an early finding on whether the Zurich series holds up around 1740.

Set up the project after TIER

☒	2.01	Create folder structure and repository

Due: Sun 18.10. · Must · Application · Program, TIER · formerly C4

☒	Folders as in section 6.3: data/input, data/intermediate, data/analysis, src, tests, scripts, reports, essay, output/figures, output/tables, output/values, docs, reference

☒	private GitHub repository; .gitignore for data/, output/, _output/, _variables.yml, .quarto/, .venv/, .idea/

☒	README.md with the eight empty sections of the Template README (section 6.4)

☒	config.yml with relative paths, period, λ values, window, lags and seed

Result: empty project after TIER in the private repository.

☒	2.02	Set up the Python environment with uv and PyCharm

Due: Sun 18.10. · Must · Application · Program · formerly C4

☒	uv init, set the Python version in .python-version

☒	uv add pandas numpy statsmodels scipy matplotlib openpyxl pyyaml regex tabulate; uv add --dev pytest (regex for the hyphenation rule, tabulate for tables as Markdown; no jupyter)

☒	pyproject.toml, .python-version and uv.lock under version control; new packages only with uv add

☒	PyCharm: open the project folder, select .venv from uv as interpreter, assign *.qmd to the Markdown file type

☒	do not install R; reference/donnerstagsnachrichten.R remains a text reference (E15)

Result: uv run pytest runs without errors (even without tests).

☐	2.03	Set up the Quarto CLI and the master script

Due: Sun 18.10. · Must · Application · Program, TIER · formerly C4

☒	Install the Quarto CLI (Fedora: .rpm, Windows: installer from quarto.org), run quarto check and record the version for the README; Jupyter and a Python engine are not needed

☐	scripts/run_all.py: runs 01 to 07 in fixed order, stops on errors, logs the run time per step, merges the key figures from output/values/ into _variables.yml and calls quarto render; option --no-render for pure data runs

☐	_quarto.yml: folders to render reports/, essay/, docs/; output to _output/; formats Typst PDF and Word; references.bib from Zotero (Better BibTeX); no pre-render

☐	Test run: render a test document with a figure from output/figures/, cross-reference, citation, embedded table and a value via {{< var >}} to PDF (Typst) and Word

☐	uv run python scripts/run_all.py runs through without errors from an empty state

☐	Create the PyCharm run configurations “Pipeline”, “Full run”, “Tests” and “Essay preview” as in section 6.3 and store them as project files in .run/

Result: One command produces the whole run; the preview in PyCharm updates on save.

☐	2.04	Store data completely and securely

Due: Sun 18.10. · Must · Application · Import · formerly C3

☒	all issues as csv (files DN and ZWB, 1730 to 1842) from OLAT to data/input/zurich/, record the number of files and issues per year with scripts/inventory.py (standalone, E16); it also checks the header of every file and flags empty files; results in output/tables/tbl-files-per-year.csv and output/values/inventory.yml

☒	weekly Basel prices to data/input/basel/; clarify file, variables, units, currency, week definition and citation, otherwise question F1 to Jakob Metzler

☒	prices_raw_public_use_zh.xlsx to data/input/chambru/

☒	donnerstagsnachrichten.R unchanged to reference/

☒	Storage as in section 5: access-protected, no public repository, no cloud without consent

☐	record provenance per source by hand in docs/provenance.yaml (source, format, date obtained, access, citation; paths via keys from config.yml); scripts/inventory.py reports missing fields and writes the tables for the README sections Data Availability and Dataset list to output/tables/

Result: all input data at the paths from section 3.1.

☐	2.05	Implement data management as in section 3.4

Due: Thu 22.10. · Must · Formalities · Plan, DMP

☒	Determine the backup location (local, access-protected, no cloud) and enter it in section 3.4: peer-to-peer sync between own devices (E17)

☒	check that git status shows no file from data/ or output/

☒	Define the format of intermediate results: csv, UTF-8, dates in ISO format; src/datafiles.py (write_csv, read_csv) and the files block in config.yml; tests/test_datafiles.py also checks that data/ and output/ stay ignored by git

☐	Create a card for the deletion after project completion (5.13)

Management and reflection

☐	2.06	Set up the Kanban board in GitHub Projects

Due: Sun 18.10. · Must · Formalities · Management

☐	Create a project with board view attached to the private repository; columns Backlog, In Progress, Waiting for Feedback, Done

☐	Fields work package, due date, must or optional; milestones M2 to M5 with date

☐	Set the limit for “In Progress” to two

☐	one card per open task from WP2 and per ongoing task Q1 to Q8, title with ID

☐	Copy the rules from section 7.4 into the project description, in particular: no data extracts

Result: Board with all cards for WP2.

☐	2.07	Complete the first Gibbs entry on the reorientation

Due: Sun 18.10. · Must · Application · Reflection

☐	review and complete the prepared entry in section 8.2, fill in Feelings personally

☐	move the action plan into cards

☐	2.08	Define criteria for gate M2 in advance

Due: Thu 22.10. · Must · Application · Decide

☐	review and adjust the target values from section 7.2 before results from the prototype are available

☐	record the decision with date in the decision log (Q1); do not change it afterwards

Organisation

☐	2.09	Secure group phase material for the essay

Due: Sun 25.10. · Must · Participation, application · formerly C1

☒	Slides, assignments and own submissions (Label Studio export, result of the prompt assignment) stored outside the repository, since the exports contain data

☐	two to three sentences per meeting in docs/group_phase.qmd: content and own contribution, for direct use in the essay

☐	record own result of the text structuring: model, strategy, F1, cost

Pipeline: Import and Tidy

☐	2.10	Build the issue register

Due: Thu 22.10. · Must · Application · Import (4.2) · formerly C5

☐	read all files (src/issues.py), date and issue ID from the file name

☐	merge advertisements across page breaks (continuation field, logic as in the R script), resolve hyphens at line ends (regex package, since re does not support \p{L})

☐	detect supplements and merge them with the main issue

☐	assign the calendar week, align the week definition with the Basel series

☐	expected versus available issues: gaps.csv; coverage per year as figure and table in output/, key figures in output/values/01.yml, embedded in reports/01_issues.qmd

☐	tests with pytest for date derivation, merging and supplements; fill in the “Status” row in 4.2

Result: issues.csv, ads.csv, gaps.csv and check report 01.

☐	2.11	Port the rubric mapping from the R scripts

Due: Sun 25.10. · Must · Application · Tidy (4.3) · formerly C6

☐	list all values of the type and rubric fields over the period and inspect them by year and title in PyCharm’s DataFrame view

☐	adopt the mapping to the scheme of the R scripts (src/rubrics.py)

☐	identify the food price rubric unambiguously for each period, produce price_lists.csv

☐	unknown headings to rubrics_unknown.csv, overview in reports/02_rubrics.qmd

☐	2.12	Check the port against R

Due: Tue 27.10. · Must · Application · Tidy (4.3) · formerly C7

☐	Sample of about ten issues from all three titles (Donnstags-Nachrichten, Donnstags-Blatt, Zürcherisches Wochenblatt)

☐	request the reference output of the R script (zwb_merged) for these issues as csv from Jakob Metzler (F8) and place it in data/intermediate/r_reference/; if it is not available by Tue 27.10., compare via pytest cases with hand-checked advertisements across page breaks and hyphens

☐	row-by-row comparison in Python, justify every deviation, agreement in reports/02_rubrics.qmd

☐	report rubrics not covered in a bundle to Prof. Woitek and Jakob Metzler (F6); card to “Waiting for Feedback”

Result: Deviations from the R version explained; “Status” row in 4.3 filled in.

Prototype and decision

☐	2.13	Prototype 1735 to 1745: Kernen price Zurich versus Basel

Due: Fri 30.10. · Must · Application · Tidy to Model · formerly C8

☐	extract the price lists 1735 to 1745, roughly extract the Kernen price

☐	cross-check two years by hand, quotation and full text side by side in PyCharm’s DataFrame view

☐	put the Basel series for the same period on the same week axis

☐	compute Δln p, first weighted correlation with RLS (λ = 0.98), one figure

☐	Metrics according to the criteria from 2.08: coverage in both cities, share of carried-forward values, share of implausible values, deviations in the hand check

☐	figure and key figures from the script to output/, embedded in reports/prototype_1735_1745.qmd

Result: Prototype report with all metrics for M2.

☐	2.14	Gate M2: Does the series hold up around 1740?

Due: Sun 1.11. · Must · Application · Decide · formerly C9

☐	answer the check questions from section 7.2, compare the metrics with the target values from 2.08

☐	if yes: continue the plan unchanged

☐	if no: agree fallback variants (later start, monthly frequency, another grain) with the supervisors, attach the prototype report as PDF, obtain a short written confirmation (F7)

☐	decision into the decision log (Q1), update tables 1.3 and 10.2, version 1.1 in Appendix C

☐	create cards for WP3

☐	Gibbs entry M2 by Wed 4.11.

Result: Decision in the decision log; WP3 released.

## 10.8 WP3 Price Parser and Validation (2 to 29 November 2026)

The goal is the Zurich weekly series over the whole period with documented measurement quality. Hand coding comes first, because the PDCA cycle needs it as a reference (E12).

Organisation

☐	3.01	Clarify form and due date of the data documentation contribution

Due: Fri 6.11. · Must · Data documentation · formerly D6

☐	ask Jakob Metzler: format, storage location, scope, due date (F2)

☐	add the answer to 2.4 and 9.2; adjust the due dates of 3.09 and 5.07

Prepare validation

☐	3.02	Hand coding: sample, coding rules, development and test sets

Due: Wed 11.11. · Must · Application · Check (4.5) · formerly D5, brought forward

☐	by Wed 4.11.: define coding rules in docs/coding_rules.qmd before coding

☐	by Wed 4.11.: sample of about 20 issues, stratified by the 1740s, 1770 and 1771, 1801, 1816 and 1817, price ranges from the 1820s, the 1840s

☐	by Wed 4.11.: split issues into development and test sets, assignment in docs/sample.csv; the parser is tuned on the development set only (as in meeting 3)

☐	by Wed 4.11.: code the price lists of the development set (good, unit, amount, flags)

☐	by Wed 11.11.: code the price lists of the test set and do not look at them again

Result: Hand coding in data/intermediate/hand_coding/, assignment under version control.

Price parser

☐	3.03	Extract quotations: good, unit, amount

Due: Fri 13.11. · Must · Application · Tidy (4.4) · formerly D1

☐	list of goods with spelling variants, found via keyword-in-context and character strings (meeting 7)

☐	resolve ditto marks

☐	price ranges from the 1820s: use the midpoint, flag the range

☐	convert amounts in Gulden, Schilling and Heller to Heller, document conversion factors with a source

☐	parser in src/prices.py; tests with pytest on quotations per period with hand-determined results

☐	Optional: extract hard-to-read lists with a language model and a fixed JSON schema, log the run as in Q5

☐	3.04	Handle special cases of the series

Due: Wed 18.11. · Must · Application · Transform (4.6) · formerly D2

☐	references to the previous week: change of zero, flag as carried forward

☐	change from Mütt to Malter: determine the date, set the change across the break to missing

☐	from 1801 the last quotation of the week; leave missing issues as gaps

☐	plausibility bands per good and decade, flag outliers and spot-check them in PyCharm’s DataFrame view

☐	3.05	PDCA iterations on the development set until stable

Due: Fri 20.11. · Must · Application, data documentation · Check (4.7)

☐	from Thu 5.11., per iteration one well-defined rule change (Plan), run (Do), metrics (Check), decision (Act)

☐	order of periods: 1740s, references to the previous week, change of 1801, price ranges, change of unit

☐	log every iteration as in Q6

☐	stop according to the stability criterion from section 4.7; tag the parser state with parser-final

Result: Validation log with all iterations; parser frozen.

☐	3.06	Zurich weekly series as intermediate result

Due: Fri 20.11. · Must · Application; condition Master · Transform (4.6) · formerly D3

☐	quotations.csv in long format: date, week, issue, good, unit, amount in Heller, flags

☐	weekly_series_zh.csv in data/analysis/; coverage 1730 to 1842 per good as a figure in reports/03_prices.qmd

☐	report phases without any price change (indication of set prices)

Validation

☐	3.07	Comparison with Chambru et al. (2026)

Due: Tue 24.11. · Must · Application · Check (4.5) · formerly D4

☐	match the Zurich observations from the newspaper by date and good

☐	share of identical values and mean deviation in reports/04_validation.qmd

☐	inspect large deviations individually and note the cause: parser, OCR or source

☐	3.08	Measurement quality on the test set

Due: Fri 27.11. · Must · Application · Check (4.5) · formerly D5

☐	evaluate the frozen parser (parser-final) once on the test set

☐	precision, recall and F1 for the quotations in reports/04_validation.qmd

☐	error analysis; later corrections only with a new iteration and a note (Q6), do not use the test set for tuning

☐	fill in the “Status” row in 4.4 and 4.5

Result: Measurement quality metrics for M3 and the essay.

Data documentation and exchange

☐	3.09	Collect the contribution to the joint data documentation continuously

ongoing until Fri 22.1. · Must · Data documentation · formerly D7

☐	in docs/data_documentation.qmd: rubric mapping and reported missing rubrics

☐	list of missing issues and supplements

☐	particularities of the price lists: references to the previous week, ditto marks, price ranges, change of unit

☐	typical OCR errors in digits and names of goods

☐	validation metrics from 3.07 and 3.08

☐	3.10	Send an interim status to the supervisors

Due: Sun 29.11. · Optional · Participation · formerly D8

☐	one page with coverage, validation and first correlation over the whole period, as a short Quarto document rendered to PDF

☐	attach open questions in a bundle (Q3)

Gate

☐	3.11	Gate M3: Kernen series complete and validated?

Due: Sun 29.11. · Must · Application · Decide

☐	answer the check questions from section 7.2

☐	Decision: proceed, proceed with restriction, or rework until Sun 6.12.

☐	decision log, tables 1.3 and 10.2, version in Appendix C

☐	create cards for WP4

☐	Gibbs entry M3 by Wed 2.12.

## 10.9 WP4 Estimation (30 November 2026 to 3 January 2027)

The goal is the results as in section 3.3. M4 freezes the core results on 16 December, the analysis is completed on 23 December, followed by a buffer over the holidays.

Merging

☐	4.01	Merge Zurich and Basel

Due: Wed 2.12. · Must · Application · Transform (4.6) · formerly E1

☐	common week axis; number of weeks with a quotation in both cities per year

☐	data/analysis/analysis_zh_bs.csv, report reports/05_weekly_series.qmd

☐	figure of the price levels of both cities (fig-prices, descriptive only)

☐	fill in the “Status” row in 4.6

Estimation as in sections 3.2 and 3.3

☐	4.02	Implement and test RLS with forgetting factor

Due: Sun 6.12. · Must · Application · Model (5.1) · formerly E2

☐	βt and exponentially weighted moments, ρt = βt σB,t / σZ,t in src/rls.py

☐	Test: with λ = 1 the last value equals the least squares estimate over all weeks; comparison with RecursiveLS from statsmodels

☐	test on simulated series with known, changing correlation

☐	define the burn-in period during which ρt is not interpreted

☐	4.03	Base estimate

Due: Wed 9.12. · Must · Application · Model (5.1) · formerly E3

☐	λ = 0.98, with and without carried-forward values

☐	bands via the Fisher transformation with the effective number of observations

☐	block bootstrap with the seed from config.yml, justify the block length

☐	Figure fig-rho

☐	4.04	Sensitivity

Due: Sun 13.12. · Must · Application · Model (5.1) · formerly E4

☐	λ = 0.96 and λ = 0.99, rolling window of 52 weeks

☐	lags of one and two weeks in both directions

☐	results as files in output/tables/, table tbl-sensitivity in report 06

☐	4.05	Benchmark episodes and limitations

Due: Wed 16.12. · Must · Application · Model, Visualize · formerly E5

☐	dearth years 1740 and 1741, 1770 and 1771, 1816 and 1817 in detail (fig-benchmarks)

☐	compare phases without price change from 3.06 with ρt (set prices)

☐	Optional: price spread ln(pZ,t / pB,t), if units and currencies can be converted

Requirements

☐	4.06	Obtain requirements for essay and technical documentation

Due: Fri 11.12. · Must · Formalities · Plan · formerly E8

☐	if nothing has arrived by Thu 10.12.: follow up (F3)

☐	clarify: scope, format, submission channel, contents of the replication package; do references and appendix count towards the length?

☐	ask whether a README after the Template README and the Quarto check reports suffice as technical documentation

☐	have it confirmed that the comparison with Basel covers the required comparison with an alternative indicator (F4)

☐	Optional: permissibility of publishing the Zurich series (F5)

☐	check the current version of the Template README and the AEA Data and Code Availability Policy

☐	adjust section 2.4, chapter 6 and WP5

Gate

☐	4.07	Gate M4: Freeze the core results

Due: Wed 16.12. · Must · Application · Decide

☐	answer the check questions from section 7.2

☐	tag the state with m4-core-results and back up the result files; afterwards only bug fixes to the core, each with an entry in the log

☐	decision log, tables 1.3 and 10.2, version in Appendix C; fill in the “Status” row in 5.1

☐	create cards for WP5

☐	Gibbs entry M4 by Sat 19.12.

Extension

☐	4.08	Further goods depending on data quality

Due: Sun 20.12. · Optional · Application · Model · formerly E6

☐	check coverage and plausibility per good in both cities

☐	add one or two goods of sufficient quality as a supplement without changing the core; justify omitting the others

☐	4.09	Count of advertisements by rubric for the appendix

Due: Sun 20.12. · Optional · Application · Visualize · formerly E7

☐	take the count from the rubric mapping, descriptive only

Completing the analysis

☐	4.10	Finalise figures and tables

Due: Wed 23.12. · Must · Application · Visualize, Communicate · formerly E9

☐	all figures and tables from section 5.2 as files in output/, with labels (fig-, tbl-) for cross-references

☐	list with ID, file and generating script for the README

☐	tag the state with analysis-final

Result: Frozen analysis state for essay and package.

☐	4.11	Buffer from 24 December to 3 January

Due: Sun 3.1. · Must · Formalities · formerly E10

☐	only complete open must tasks from WP2 to WP4, do not start new analysis

☐	the state analysis-final remains frozen

## 10.10 WP5 Essay and Replication Package (4 to 29 January 2027)

The goal is the complete submission on Friday, 29 January 2027. Format and scope follow the requirements from 4.06. Essay, codebook and data documentation are rendered from Quarto documents.

Prepare the essay

☐	5.01	Outline with page budget

Due: Wed 6.1. · Must · Application · Communicate · formerly F1

☐	essay/essay.qmd outlined as in section 6.2, labels (sec-) for the sections

☐	plan the group work using the notes from 2.09 (docs/group_phase.qmd)

☐	assign figures and tables from 4.10 to the sections

☐	set the page format according to the requirements from 4.06 and check with a test run how much text eight pages hold

Package and data delivery

☐	5.02	Complete the README after the Template README

Due: Fri 8.1. · Must · Application · Communicate, TIER · formerly F5

☐	fill in all eight sections as in section 6.4

☐	Data Availability: expected paths, format and provenance of the raw data; raw data are not included (section 2)

☐	Computational requirements: versions of uv, Python, packages (uv.lock) and the Quarto CLI, run time, hardware; note that neither Jupyter nor R is required

☐	steps using a language model: model, version, prompt, parameters, cost (from Q5)

☐	List of tables and figures from 4.10

☐	5.03	Zurich series in the format of the price database with codebook

Due: Wed 13.1. · Must · Application; condition Master · Communicate · formerly F7

☐	adopt fields and coding of the price database (scripts/07_export.py)

☐	Codebook docs/codebook.qmd: variables, units, flags, provenance, citation note

☐	check the export file for completeness and plausibility; tick off the FAIR criteria from section 3.4

Result: zurich_price_database.csv and codebook as PDF.

☐	5.04	Gate M5: clean run in a fresh environment

Due: Fri 15.1. · Must · Application · Control · formerly F6, brought forward

☐	Procedure as in section 6.5: fresh clone, raw data at the paths, uv sync --locked, uv run python scripts/run_all.py from the command line, without PyCharm

☐	compare result files with analysis-final; run time into the README

☐	no raw data and no reconstructable data in the package; check rendered reports for data extracts

☐	Decision as in section 7.2: release or rework until Wed 20.1.; decision log, version in Appendix C

☐	Gibbs entry M5 by Mon 18.1.

Writing the essay and data documentation

☐	5.05	First draft of the essay

Due: Sun 17.1. · Must · Application · Communicate · formerly F2

☐	all sections written out in essay.qmd

☐	result numbers in the text only via {{< var >}} from _variables.yml, none entered by hand

☐	limitations from section 3.5 included: early period, set prices, OCR, common shocks

☐	5.06	References and source citations

Due: Wed 20.1. · Must · Application · Communicate · formerly F3

☐	cite data sources as in Table 1 of the agreement (section 4); Basel series according to the source of the Avis project

☐	keep the literature in Zotero, export as .bib (Better BibTeX), include a CSL style; Quarto lists only cited titles

☐	position Federico (2012) and Grimmer et al. (2022)

☐	5.07	Complete the contribution to the joint data documentation

Due: Fri 22.1. · Must · Data documentation · formerly F8

☐	docs/data_documentation.qmd from 3.09 rendered in the form required by 3.01 and submitted

☐	if the due date from 3.01 is earlier, bring it forward accordingly

☐	5.08	Revision

Due: Sun 24.1. · Must · Application · Communicate · formerly F4

☐	keep to the length of eight pages in the rendered PDF

☐	check that every result number comes via {{< var >}}

☐	condense the reflection part from chapter 8, if the requirements provide for one

☐	Optional: have it proofread, rendering a Word version from the same source for this

☐	attach a declaration of independent work and AI tools, including coding assistants (Q5), if required

Submission

☐	5.09	Final run in a fresh environment

Due: Wed 27.1. · Must · Application · Control

☐	procedure as in 5.04 with the submission state; tag the state with submission

☐	The essay renders without warnings on cross-references and citations

☐	5.10	Final check

Due: Thu 28.1. · Must · Formalities · formerly F9

☐	all parts complete as in section 6.1 and the coverage in 10.3

☐	file names and submission channel according to the requirements from 4.06

☐	bring this documentation to its final state (Q8)

☐	5.11	Submission

Due: Fri 29.1. · Must · Formalities · formerly F10

☐	submit essay, replication package, Zurich series and contribution to the data documentation

☐	file the confirmation of receipt

After submission

☐	5.12	Final reflection on the whole project

Due: Sun 31.1. · Optional · Application · Reflection

☐	Gibbs entry “Final” in section 8.3

☐	record lessons for the Bachelor thesis

☐	5.13	Handle the data as in section 5 of the agreement

after project completion · Must · Formalities · formerly F11

☐	delete personal copies of the provided data, including in data/intermediate/, data/analysis/, _output/ and in backups

☐	or obtain permission for further retention beforehand

☐	5.14	Check the credit of the 6 ECTS

after grading · Must · Formalities · formerly F12

# Appendix A: Mapping to IPERKA

The table shows where each IPERKA phase is covered in the framework and in this documentation.

| IPERKA | Element in the framework | Place and result in the project |
| --- | --- | --- |
| Inform | PPDAC Problem; review of sources and literature | Chapter 2, section 3.1 |
| Plan | PPDAC Plan; work packages, Gantt; lean DMP | Chapters 3 and 7 |
| Decide | Milestones as gates | Section 7.2; gates 1.04, 2.14, 3.11, 4.07, 5.04 |
| Realise | PPDAC Data and Analysis; R4DS cycle; TIER structure | Chapters 4 and 5, section 6.3 |
| Control | PDCA micro-cycle; run in a fresh environment | Sections 4.5, 4.7 and 6.5; validation log |
| Evaluate | PPDAC Conclusion; Gibbs’ Reflective Cycle | Chapters 6 and 8; essay, reflection entries, README |

# Appendix B: Confirmed Email of 12 October 2026

Summary of the meeting of 7 October 2026 sent to Prof. Woitek and Jakob Metzler, confirmed by Jakob Metzler on 12 October 2026. Original wording (German):

Lieber Herr Woitek, lieber Jakob

Vielen Dank für die Besprechung vom 7. Oktober. Ich habe die Ergebnisse festgehalten und möchte mich vergewissern, dass ich alles richtig verstanden habe, bevor ich mit der Umsetzung beginne.

Neue Ausrichtung

Die Arbeit untersucht, ob zwischen den Getreidemärkten von Zürich und Basel bereits um 1740 eine Marktintegration bestand und wie sie sich bis 1842 entwickelte. Gemessen wird dies an der Korrelation der wöchentlichen Preisänderungen beider Städte, die ich mittels RLS als Zeitreihe von Korrelationskoeffizienten schätze.

Die Zürcher Reihe stammt aus den amtlichen Preisnotierungen der Donnstags-Nachrichten, die Basler Reihe übernehme ich aus dem Avis-Projekt. Ich beginne mit dem Getreide, zunächst dem Kernen, und nehme weitere Güter schrittweise auf, sobald ihre Datenqualität einen Vergleich zulässt.

Die Anzeigenstruktur, die Datierung von Wendepunkten, der Vergleich mit den Reihen von Pfister und das VAR-Modell aus meinem Konzept würde ich nicht weiterverfolgen. Die Zuordnung der Rubriken bleibt nötig, um die Preislisten aufzufinden.

Stand der offenen Punkte

– Rubrikenschema: Massgeblich sind die R-Skripte. Nicht erfasste Rubriken melde ich Ihnen/Euch.

– Basler Preise: Liegen aus dem Avis-Projekt fertig vor.

– Pipeline: Ich setze sie ausschliesslich in Python um und nutze den vorhandenen R-Code als Referenz.

– Sprachmodelle (Ziffer 3 der Vereinbarung): Die Zustimmung liegt vor.

– Zusätzliche Preisdaten für den Master: Ich gehe davon aus, dass die wöchentliche Zürcher Getreidereihe im Format der Preisdatenbank genügt.

– Essay und technische Dokumentation: Die Vorgaben folgen bis Dezember.

Können Sie mir bestätigen, dass ich das so richtig verstanden habe? Dann würde ich mit der Umsetzung beginnen.

Freundliche Grüsse

Gregor Lushaj

# Appendix C: Change History

| Version | Date | Change |
| --- | --- | --- |
| 1.0 | 15.10.2026 | Rebuilt along the planning framework of 14.10.2026. Replaces the “Dokumentation Donnerstag-Nachrichten” (as of 15.10.2026), which is kept as an archive. New decisions E09 to E13; checklist by work package with new IDs. |
| 1.0.1 | 26.10.2026 | Working environment PyCharm instead of Positron, Quarto CLI for writing only, no R (E14, E15). Section 6.3 extended by working with PyCharm and the Quarto CLI; master command uv run python scripts/run_all.py; question F8. Adjusted: sections 2.4, 3.5, 4.1 to 4.3, 5.2, 5.3, 6.3 to 6.5, 7.2; tasks Q2, Q5, 2.01 to 2.03, 2.10 to 2.13, 3.04, 5.02, 5.04, 5.05 and 5.08. |
| 1.0.2 | 26.10.2026 | Documentation translated into English. File names, figure and table IDs, tags and options of the pipeline renamed to English (e.g. src/issues.py, quotations.csv, fig-benchmarks, analysis-final, --no-render); work packages renamed WP0 to WP5; Gantt symbols S (submission) and B (buffer). Appendix B keeps the original German wording of the confirmed email. |
| 1.0.3 | 29.10.2026 | Task 2.04 implemented: standalone script scripts/inventory.py and hand-filled docs/provenance.yaml (E16). Adjusted: section 6.3 (docs/), task 2.04, decision log. |
| 1.0.4 | 29.10.2026 | Appendix D with the research data use agreement. Provenance per source recorded in docs/provenance.yaml: Basel series identified (Avis project, Zenodo v1.0.0), Chambru et al. checked against Table 1. Adjusted: section 3.1, question F1, new question F9, sources.provenance.yaml (E16). Adjusted: section 6.3 (docs/), task 2.04, decision log. |
| 1.0.5 | 29.10.2026 | Task 2.05 implemented: backup location in section 3.4 (peer-to-peer sync between own devices), format of intermediate results via src/datafiles.py and config.yml, git check in tests/test_datafiles.py (E17). The card for 5.13 follows with the board in 2.06. Adjusted: section 3.4, task 2.05, decision log. |
| 1.1 |  | after gate M2 |
| 1.2 |  | after gate M3 |
| 1.3 |  | after gate M4 |
| 1.4 |  | after gate M5 |
| 2.0 |  | Final state for submission |

# Appendix D: Research Data Use Agreement

Data sheet and agreement on the use of research data in the project, signed by Gregor Lushaj (place and date on the form: Zürich, 14.09.2025) and sent to Prof. Woitek; the signed copy is docs/daten_agreement.pdf. This documentation cites its sections as “agreement, section 1” to “section 5”; citations follow Table 1. Not listed in Table 1 are the Zurich issue files (DN, ZWB) and the course R script (question F9), and the Basel series, which is published under CC BY-NC-SA 4.0 (section 3.1). Original wording (German):

Datensätze

Das Verzeichnis daten enthält die Datensätze zur ökonomischen Aktivität im Kanton Zürich, die eventuell für Ihr Projekt interessant sein könnten.

Tabelle 1: Datenquellen

| Quelle | File |
| --- | --- |
| Pfister (1985) | various_production_zehnten_ch_1529_1825.xls |
| Pfister (1992) | Pfundzolleinnahmen.xlsx |
| Chambru et al. (2026) | prices_raw_public_use_zh.xlsx |
| Chambru et al. (2026) | various_production_waser_thermometer_1550_1770.xlsx |

• various_production_zehnten_ch_1529_1825.xls: Zehntdaten für verschiedene Landvogteien, die wir im notebook konjunktur_zh_18.ipynb bearbeitet haben.

• Pfundzolleinnahmen.xlsx: Exportzoll für Zürich, zur Verfügung gestellt von Ulrich Pfister (Pfister, 1992).

• prices_raw_public_use_zh.xlsx: Preise verschiedener Güter im Kanton Zürich, 1700-1970.

• various_production_waser_thermometer_1550_1770.xlsx: Wasers Zehntdaten, die wir im notebook waser_tithe_cycle_solution.ipynb bearbeitet haben.

Wenn Sie die Daten nutzen wollen, dann gelten die Regeln der Nutzungsvereinbarung (siehe nächste Seite). Bitte unterschreiben Sie die Vereinbarung und senden Sie an pdf an Ulrich Woitek (ulrich.woitek@econ.uzh.ch).

Vereinbarung zur Nutzung von Forschungsdaten

Die im Rahmen des Projekts Donnstags-Nachrichten (Zürich, 1730–1842) - Digitalisierung und Konjunkturindikatoren zur Verfügung gestellten Daten dürfen ausschliesslich für die Bearbeitung des laufenden Projekts verwendet werden.

Mit der Nutzung der Daten verpflichte ich mich, folgende Bedingungen einzuhalten:

1. Zweckgebundene Nutzung

Die Daten werden ausschließlich für die Bearbeitung des oben genannten Projekts verwendet. Eine Nutzung für andere Zwecke bedarf der vorherigen Zustimmung von Ulrich Woitek.

2. Keine Weitergabe oder Veröffentlichung

Die Daten dürfen weder vollständig noch auszugsweise an Personen ausserhalb der Projektgruppe bzw. Lehrveranstaltung weitergegeben, veröffentlicht oder auf öffentlich bzw. für Dritte zugänglichen Plattformen bereitgestellt werden. Dies gilt auch für bearbeitete oder daraus abgeleitete Datensätze, soweit daraus die bereitgestellten Daten rekonstruiert werden können.

3. Externe Dienste

Die Daten dürfen nicht ohne vorherige Zustimmung auf externe Dienste hochgeladen werden, insbesondere nicht auf öffentlich zugängliche Cloud-Plattformen oder KI-Dienste.

4. Quellenangabe

Bei jeder Verwendung von Ergebnissen, die auf dem Datensatz beruhen, sind die Quellenangaben aus Tabelle 1 zu verwenden.

5. Aufbewahrung und Löschung

Die Daten sind so aufzubewahren, dass ein Zugriff durch unbefugte Dritte verhindert wird. Nach Abschluss des Projekts sind sämtliche persönlichen Kopien der bereitgestellten Daten zu löschen, sofern keine ausdrückliche Genehmigung zur weiteren Aufbewahrung oder Nutzung erteilt wurde.

Mit meiner Unterschrift bestätige ich, dass ich diese Bedingungen zur Kenntnis genommen habe und einhalten werde.

Name: Gregor Lushaj · Ort, Datum: Zürich, 14.09.2025 · Unterschrift: vorhanden (docs/daten_agreement.pdf)

Literatur

Chambru, C., Baltensperger, M., Hediger, S., Metzler, J., und Woitek, U. (2026), “Datenbank.”, SNF Projekt Measuring Economic Growth and Welfare in 19th Century Switzerland.

Pfister, C. (1985), Klimageschichte der Schweiz 1525-1860. Das Klima der Schweiz und seine Bedeutung in der Geschichte der Landwirtschaft. Zweite Ausg., Bern: Paul Haupt.

Pfister, U. (1992), Die Zürcher Fabriques. Protoindustrielles Wachstum vom 16. zum 18. Jahrhundert. Zürich: Chronos Verlag.

# Sources

Burghartz, S., Bannert, M., Dickmann, L., Decker, E., Engel, A., Reimann, A. and Serif, I. (2023), “Raw and Processed Data of Printed Markets – The Basel Avisblatt (1729-1845)”, version 1.0.0, Zenodo, doi:10.5281/zenodo.8278751. Repository: github.com/avisblatt/avisdata. Licence CC BY-NC-SA 4.0.

Chambru, C., Baltensperger, M., Hediger, S., Metzler, J. and Woitek, U. (2026), “Datenbank”, SNSF project Measuring Economic Growth and Welfare in 19th Century Switzerland.

Federico, G. (2012), “How Much Do We Know about Market Integration in Europe?”, Economic History Review 65, 470–497.

Gibbs, G. (1988), Learning by Doing: A Guide to Teaching and Learning Methods, Oxford: Further Education Unit.

Grimmer, J., Roberts, M. E. and Stewart, B. M. (2022), Text as Data: A New Framework for Machine Learning and the Social Sciences, Princeton: Princeton University Press.

Lushaj, G. (2026), Planungsgerüst für das Research Lab Donnstags-Nachrichten: Marktintegration Zürich–Basel, 1740 bis 1842 [planning framework], as of 14 October 2026.

Project TIER (n.d.), TIER Protocol 4.0, Haverford College. projecttier.org/tier-protocol/protocol-4-0/

Swiss National Science Foundation (2017), Data Management Plan (DMP): Guidelines for researchers. snf.ch

Shewhart, W. A. (1939), Statistical Method from the Viewpoint of Quality Control, Washington: Graduate School of the Department of Agriculture.

Social Science Data Editors (2020), “A template README for social science replication packages”. social-science-data-editors.github.io/template_README/

Wickham, H., Çetinkaya-Rundel, M. and Grolemund, G. (2023), R for Data Science, 2nd edition, Sebastopol: O’Reilly. r4ds.hadley.nz

Wild, C. J. and Pfannkuch, M. (1999), “Statistical Thinking in Empirical Enquiry”, International Statistical Review 67(3), 223–265.

Wilkinson, M. D. et al. (2016), “The FAIR Guiding Principles for scientific data management and stewardship”, Scientific Data 3, 160018.